## Tabelle1
EEB Feature List
| feature | status in EEB 5.5.0 | status in EEB 6 | has to be in initial EEB6 release | finished at | priority (FK) | assignment potential (FK) | description
licensing
| wibu protection | Released | TBD | x | End of August | high |  | Creation of HW dongles and encryption routines for deployment process (installer packages)
| borrowable licenses | Released | TBD | x | End of August | high |  | Creation of configuration files (*.wbb) and integration into deploy process for installer packages
data interfaces
| open HCV | Released | Done | x |  | high
| save HCV | Released | TBD | x | Mid of July | high |  | Integrate redlining information into HCV (depends on how redlining functionality should be implemented)
| import KBL | Released | TBD | x | End of June | mid |  | Open pure KBL file within EEB application
| export raster graphics (bmp,jpg,png ...) | Released | Done | x |  | mid
| export vector graphics (dxf, dwg, svg ...) | Released | Done | x |  | mid
| export PDF | Released | Done | x |  | mid
| print | Released | Done | x |  | high
drawing
| drawing navigation (zoom, pan, etc) | Released | Done | x |  | high
| navigation view | Released | Done | x |  | mid
| display drawing in 3D | - | TBD |  |  | mid
grid
| sort | Released | Done | x |  | mid
| filter | Released | Done | x |  | mid
| configure displayed data columns (hide/unhide) | Released | Done | x |  | mid
| cross selection | Released | Done | x |  | high
| export grid data | Released | Done | x |  | high
configuration
| import module configuration | - | TBD |  | End of July | high |  | Simple copy/paste of a bunch of part numbers which should be activated inside a opened document - rest has to be deactivated
| module tree | Released | Done | x |  | high
| configure module tree | Released | Done | x |  | mid
| hide objects in drawing and grid in respect to configuration | Released | Done | x |  | high
| show modules for object | Released | Done | x |  | mid
| save module tree configuration | Released | Done | x |  | high
analysis
| show start/end connectors | Released | Done | x |  | high
| find | Released | Done | x |  | mid
| connectivity view | Released | Done | x |  | high
| connectivity view for whole module | - | TBD |  |  | mid | low
| compare designs | Released | Done | x |  | mid
| Analyse View - Show Options | Released | TBD |  |  | mid
| Analyse View - Show Diameter | Released | TBD |  |  | low
| Analyse View - Show Wet/Dry | Released | TBD |  |  | low
| Analyse View - Show Plating Material | Released | TBD |  |  | mid |  | To be discussed if necessary for first release version
| Analyse View - Show Environment | Released | TBD |  |  | low
| Analyse View - Show Splices | Released | TBD |  |  | mid |  | To be discussed if necessary for first release version
| Analyse View - Show Eylets | Released | TBD |  |  | low
| BOM View | Released | Done | x |  | high
| bundle calculation and visualization | - | TBD |  |  | mid | mid
| copper content view | Released | TBD |  |  | low
red lining
| textual redlinig | Released | TBD | x | Mid of June | high
| graphical redlining | Released | TBD |  |  | mid
| import red lining | - | TBD | x | End of July | high |  | How Daimler want to interchange redlining information with different HCV documents???
display whole car
| open several HCVs | Released | Done | x |  | high
| cross selection between different HCVs | - | TBD |  |  | high | high
| navigation view for whole car | - | TBD |  |  | mid | high
miscallaneous
| plugin interface | - | TBD |  |  | low
| general settings | - | Done | x |  | mid
help
| take screenshots | Released | TBD | x | Begin of September | high |  | Has to be done by Fabian and Thomas
| create manual | Released | TBD | x | Begin of September | high |  | Has to be done by Fabian and Thomas
installer package and deployment
| create two separate installer packages for EEB (x86 and x64) |  |  |  | Mid of September | high
| RELEASE DATE | End of September